[image: image1.emf]Committee Officers and Key Contacts
September 1, 2009 – August 31, 2010
	Committee Name

	Information Technology
	Submission Contact Name:
	Karen W. Craig

	Chair


	Karen W. Craig
	Submission Contact E-mail
	craig@tuskegee.edu

	Vice-Chair


	Steven Garner
	Submission Contact Phone
	(334) 724-4856

	Secretary


	Terrence Wolfork
	Date of Submission
	August 27, 2009

	PLC Representative 1862

	Jim Segers
	PLC Representative 1890
	Lalit Rainey

	1862 Advisor
	Jimmy Henning
	1890 Advisor


	(n/a)


Annual Plan of Work

September 1, 2009 – August 31, 2010
	Cross Committee Issue Addressed, if applicable*
	Item to Accomplish


	Responsibility

(Names of people assigned to item)
	Key Contact

(Person who will serve as a key contact for item)
	Goal Date

(Anticipated completion date)
	Completion Date 

(fill in when completed)

	
	Work with committee advisor to continue to identify PLN IT representatives from states which have not been represented recently and to encourage their participation.  Participation would include conference calls, virtual meetings, etc.
	All  IT Committee Members 
	Jim Segers
	July 2010
	

	
	Continue to maintain the resource list of social networking tools which is available on the eXtension web site at http://collaborate.extension.org/wiki/Web2
	All IT Committee Members
	Anne Adrian
	July 2010
	

	2
	Best Practices and Processes for Americans with Disabilities Act  compliance; including a training module
	All IT Committee Members
	Chris Adcock
	July 2010
	

	3,4
	Continue communicating and promoting eXtension activities to our state constituents

· Develop  iTeams and promote iTeam involvement 

· Clearly define IT's role within the iTeam 

· Continue to pilot and receive feedback from Ask an Expert widget in appropriate web community sites (county or content teams) 

· Encourage use of FAQ database 
	All IT Committee Members
	(Individual Efforts)
	July 2010
	

	
	Program Committee Collaboration and Partnerships.

· Offer an IT representative to be present on each committee’s calls
	All IT Committee Members
	Dwayne Hunter
	July 2010
	

	2,3,4
	Work with Communications Committee to conduct webinars

	All IT Committee Members
	Karen Craig
	December 2009
	

	4, 10
	Establish and promote better working (more dialogue) relationship between IT staff and other extension personnel.
	All Committee Members
	Lalit Rainey
	July 2010
	



Submission instructions:  


Rename the document with your committee name initials (ANR, CRD, COM, FCS, 4H, ITS, MM, PSD, PLC) such as:  ANRplanofwork.doc  


Email document to the SRDC to Rachel Welborn at � HYPERLINK "mailto:rachelw@srdc.msstate.edu" �rachelw@srdc.msstate.edu�


If you have problems, call Rachel at 662-325-3207.  Rachel will verify receipt of each Plan of Work as it is received.








*Cross Committee Issues:  

INTERNAL:  1. Human Capital, 2. Organizational Relevance, 3. Physical Resources, 4. Technology

EXTERNAL:  5. Wholesome & Safe Food Supply, 6. Benchmarking Impacts, 7. Energy, 8. Health Education, 9. Leadership Development, 10. Natural Resource Base 


