Family & Consumer Science
Plan of Work

2007-08

	Chair during Plan Year: Shirley Hastings
Contact: hastings@utk.edu
	2007-2008 Annual Work Plan
September 1, 2007 -- August 31, 2008

	Update FCS List Serve
Responsibility: Shirley Hastings/ Kathy Ibendahl 
Goal Date: October 2007 
Completion Date: 9/28/07

	Forward Minutes to SRDC Office
Responsibility: Shirley Hastings
Goal Date: October 2007 
Completion Date: 10/19/07

	Convene Quarterly FCS Conference Calls
Responsibility: Shirley Hastings/ Officers/ Committee 
Goal Date: October 2007 
Completion Date:

	Submit Annual Plan of Work
Responsibility: Shirley Hastings
Goal Date: October 2007 
Completion Date: 10/26/07

	Inventory of Southern Region Health Curriculum
Responsibility: Judy Warren
Goal Date: December 2007
Completion Date:

	Survey of Southern Region Childhood and Youth Obesity Prevention Curriculum
Responsibility: Katherine Cason and Eunice Bonsi
Goal Date:
Completion Date:

	Plan/ Conduct a Meeting of Southern Region FCS Program Leaders 
Responsibility: Shirley Hastings/ Officers/ Committee
Goal Date: Spring 2008
Completion Date:

	Explore/ Plan Feasibility of a Health Disparities Workshop
Responsibility: Evelyn Crayton, Carolyn Nobles and Krystal Smith
Goal Date: August 2008
Completion Date:

	Conduct 08 FCS Committee Meeting
Responsibility: Shirley Hastings/ Officers/ Committee
Goal Date: August 2008 
Completion Date:

	Southern Region CECP Module Development
Responsibility: Jorge Atiles
Goal Date: December 2008
Completion Date:



Submission instructions				 Due Date: August 28, 2008 





Save document as FCSupdate.doc


Email file to Rachel Welborn at � HYPERLINK "mailto:rachelw@srdc.msstate.edu" �rachelw@srdc.msstate.edu�


If you have questions or problems, contact Rachel at 662-325-3207














