New Committee Officers and Key Contacts

September 1, 2018 – August 31, 2019

| Committee Name | Community Resource Development | Submission Contact Name: | Stacey McCullough |
| --- | --- | --- | --- |
| Chair | Stacey McCullough | Submission Contact E-mail | smccullough@uaex.edu |
| Vice-Chair | Iris Crosby | Submission Contact Phone | 501-671-2078 |
| Secretary | Alison Davis | Date of Submission | 8/23/18 |
| PLC Representative 1862 | Mark Waller | PLC Representative 1890 | Iris Crosby |
| 1862 Advisor | Ed Jones | 1890 Advisor | Tasha Hargrove |

Annual Plan of Work

September 1, 2018 – August 31, 2019

| Item to Accomplish | Responsibility | Key Contact | Goal Date | Completion Date (fill in when complete) |
| --- | --- | --- | --- | --- |
| CRD proposes to take the leadership role in engaging the other committees to develop a concept paper and steps to help position Extension for the future. | Alison, Stacey, Joy, Dave, Dan, Mark, Steve | Stacey McCullough | October 2018 (continuation) |  |
| Regional summary of each institution’s programs and resources related to items in the President’s Interagency Task Force on Agriculture and Rural Prosperity. | Keith, Sreedhar, Rachel, Joy, Steve, Russ All program leaders | All Program Leaders Alison Davis Joy Moten-Thomas | December 2018 |  |
| Share CRD programming across the region through the following: - Host monthly webinar series. - Contribute to one issue of SRDC’s Around the South newsletter highlighting program and person. | All Program Leaders | All Program Leaders Rachel Welborn | July 2019 |  |
| Continue in CRD indicator work and growth and explore opportunities for greater participation: - Collect data for 2018-2019 and create a regional report (From CRD & FCS) | Rachel, Susan, Sreedhar, Mark, Alison, Jimmy | Sreedhar Upendram | July 2019 |  |
| Continue conversation with Middle Managers (including PSD representation) pertaining to CRD 101 training. Offer a multi-state CRD 101 agent training. | Susan, Alison, Rachel, Stacey, Sreedhar, Crystal, Dan, Gill, Jimmy | Stacey McCullough Alison Davis | July 2019 July 2019 |  |
| Heirs Property - FCS and CRD leaders will work collaboratively with existing heirs property efforts being led by SRDC and their collaborative partners to explore the issues and leadership needed relative to family heirs property in the southern region. | Joint CRD/FCS committee members | Sandra Thompson (CRD) Jorge Atiles (FCS) | December 2018 |  |
| Economic Mobility - FCS and CRD will conduct inventory of existing programs, collaborative efforts and opportunities for future collaboration in areas of entrepreneurial development, workforce development, and built environment. | Joint CRD/FCS committee members | Stacey McCullough (CRD) Mike Gutter Laura Stephenson (FCS) | July 2019 |  |
| Food Systems - a subcommittee of FCS and CRD leaders will conduct a conference call on September 10, 2018 to further discuss food systems work prior to the SERA-47 meeting. | Joint CRD/FCS committee members | Michelle Eley (CRD) (FCS) Leslie Speller-Henderson Virginie Zoumenou | September 2018 |  |
| Develop a list of CRD priorities to present at NIFA’s Town Hall meeting scheduled for October 26th in New Orleans, LA, and via survey link. | Alison Davis, Stacey McCullough, Joy Moten-Thomas | Stacey McCullough | December 2018 |  |

Conference Call Schedule:

October 17, 2018

December 19, 2018

February 21, 2019

April 17, 2019

June 19, 2019

July 17, 2019

*All Conference Call Times at 1:00 PM Central/2:00 PM Eastern/3:00 PM Atlantic