New Committee Officers and Key Contacts

September 1, 2025 – August 31, 2026

(See submission instructions at end of document)

| Committee Name | Communications | Submission Contact Name: | Sue Smith |
| --- | --- | --- | --- |
| Chair | Tracy Courage, University of Arkansas, tcourage@uada.edu | Submission Contact E-mail | suesmith@uga.edu |
| Vice-Chair | Vickey D. Williams, Alcorn State University, vwilliams@alcorn.edu | Submission Contact Phone | 706-518-9078 |
| Secretary | Sue Smith, University of Georgia suesmith@uga.edu | Date of Submission | August 18, 2026 |
| PLC Representative 1862 | Chris Elam, Texas A&M, chris.elam@ag.tamu.edu (2027) | PLC Representative 1890 | Erica Shambley, Virginia State University, eshambley@vsu.edu (2028) |
| 1862 Advisor | Justin Rhinehart, University of Tennessee | 1890 Advisor | Mark Latimore, Jr., Fort Valley State, latimorm@fvsu.edu |

Annual Plan of Work

September 1, 2025 – August 31, 2026

| Item to Accomplish | Responsibility (Names of people assigned to item) | Key Contact (Person who will serve as a key contact for the item) | Goal Date (Anticipated completion date) | Completion Date (to be filled in when completed) |
| --- | --- | --- | --- | --- |
| Develop a module and a one-page guide for Marketing Local Programs Internal Marketing Local Programs | Chris Elam, Vickey D. Williams; adding Sue Smith | Chris Elam | February 2026 | Will roll into 2026-27; November 2026 for the survey completion; complete 1-pager by July 2027 |
| Create Guidelines for Responsible and Effective Use of AI in Marketing & Communications | Vickey D. Williams, Erica Shambley, Latasha Everson, Sonya Moore-Davis | Deseray McKinzy | August 2026 | Will roll into August 2027; information compiled and guidelines started |
| Develop a Responsible AI Toolkit for Faculty, Researchers, and Extension Professionals | Vickey D. Williams, Erica Shambley, Latasha Everson, Sonya Moore-Davis | Vickey Williams | August 2026 | Will roll into 2026-27. |
| Accessibility Module and Training - Overview, guidelines, and best practices. - Generalized best practices and standards. - Accessibility standards change in April 2026. | Vickey D. Williams, Lori Greiner, Hayley Pierce, Stacy Herrick, Matt Browning, Lyndall Stout, Mariah Spiva, | Stacy Herrick | August 2026 | Modules already created at an institution will be shared with the group; remaining work will roll into 2026-27. |
| Capture and amplify success stories of member institutions for collaborative quarterly news releases. (one pager) - Outline process - Standards of Operations | Frankie Gould, Tobie Blanchard, Tracy Courage, Matt Browning, Lyndall Stout, & Latasha Everson, Brian Utley | Frankie Gould | November 2026 | Outline of process was complete by August 2026; standards and stories will roll into 2027. |
| Develop a new PLN digital brand. - Create a new image (brand kit for Logo) | Amy Carpenter-Driscoll, Tracy Courage, Carmen Kelly, Marquinta Gonzalez | Tracy | January 2026 | In progress as of August 2026; will complete in 2026-27. |

Quarterly Conference Call Schedule:  (Dates/Times – Please indicate time zone)

November 6, 11 AM EST

January 15, 11 AM EST

April 9, 11 AM EST

July 9, 11 AM EST

Submission instructions:

Rename the document with your committee name initials (ANR, CRD, COM, FCS, 4H, ITS, MM, PSD, PLC) such as:  ANRplanofwork.doc

Email document to HYPERLINK "mailto:r.scammahorn@msstate.edu"r.scammahorn@msstate.edu

If you have problems, contact Roseanne Scammahorn at HYPERLINK "mailto:r.scammahorn@msstate.edu"r.scammahorn@msstate.edu